## Priority 3 Sprint 4 Internal
[8 empty] | 2021-05-21 |  |  | 2021-04-01 | [29 empty] | 2021-05-01
[8 empty] | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
No | Task Name | Duration | Status | Start | Finish | Resource Names | Completed | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
1 | Requirement Collection & Documentation | 35 days | Closed |  | 2021-03-02 | Seyha I. | 100% | 2021-04-01 We 14: Cambodia's Holiday (Khmer New Year); 2021-04-01 Mo 26: Cambodia's Holiday (វិសាខបូជា); 2021-04-01 Fr 30: Cambodia's Holiday (ច្រត់ព្រះនង្គ័ល); 2021-05-01 Sa 1: Cambodia's Holiday (ពលកម្មអន្ដរជាតិ); 2021-05-01 Fr 14: Cambodia's Holiday (ទិវានៃការចាំ)
1.1 | Business Requirement Collection | 22 days | Closed |  |  |  | 100%
1.2 | Requirement and Sign (FSD) | 10 days | Closed |  |  |  | 100%
2 | MIS Team Development | 24 days | In-Progess | 2021-03-29 | 2021-05-05 | Kin | 50% | bar: 2021-05-21 Mo 29 to 2021-04-01 Fr 2; 2021-04-01 Mo 5 to 2021-04-01 Fr 9; 2021-04-01 Mo 12 to 2021-04-01 Tu 13; 2021-04-01 Mo 19 to 2021-04-01 Fr 23; 2021-04-01 Tu 27 to 2021-04-01 Th 29; 2021-05-01 Mo 3 to 2021-05-01 We 5
2.1 | Mobile Development | 24 days | In-Progess | 2021-03-29 | 2021-05-05 | Em, Chanthourn | 50% | bar: 2021-05-21 Mo 29 to 2021-04-01 Fr 2; 2021-04-01 Mo 5 to 2021-04-01 Fr 9; 2021-04-01 Mo 12 to 2021-04-01 Tu 13; 2021-04-01 Mo 19 to 2021-04-01 Fr 23; 2021-04-01 Tu 27 to 2021-04-01 Th 29; 2021-05-01 Mo 3 to 2021-05-01 We 5
2.2 | Tab Switch And Backend Development | 24 days | In-Progess | 2021-03-29 | 2021-05-05 | Roth, Kin | 50% | bar: 2021-05-21 Mo 29 to 2021-04-01 Fr 2; 2021-04-01 Mo 5 to 2021-04-01 Fr 9; 2021-04-01 Mo 12 to 2021-04-01 Tu 13; 2021-04-01 Mo 19 to 2021-04-01 Fr 23; 2021-04-01 Tu 27 to 2021-04-01 Th 29; 2021-05-01 Mo 3 to 2021-05-01 We 5
2.3 | Tab Switch And Backend Development | 24 days | In-Progess | 2021-03-29 | 2021-05-05 | Roth, Kin | 50% | bar: 2021-05-21 Mo 29 to 2021-04-01 Fr 2; 2021-04-01 Mo 5 to 2021-04-01 Fr 9; 2021-04-01 Mo 12 to 2021-04-01 Tu 13; 2021-04-01 Mo 19 to 2021-04-01 Fr 23; 2021-04-01 Tu 27 to 2021-04-01 Th 29; 2021-05-01 Mo 3 to 2021-05-01 We 5
24 | Hot fix change disbursement date |  | In-Progess |  | 2021-05-05 | Roth, Kin | 70% | bar: 2021-05-21 Mo 29 to 2021-04-01 Fr 2; 2021-04-01 Mo 5 to 2021-04-01 Fr 9; 2021-04-01 Mo 12 to 2021-04-01 Tu 13; 2021-04-01 Mo 19 to 2021-04-01 Fr 23; 2021-04-01 Tu 27 to 2021-04-01 Th 29; 2021-05-01 Mo 3 to 2021-05-01 We 5
3 | SIT | 8 days | To-do | 2021-05-06 | 2021-05-18 | Pheara | bar: 2021-05-01 Th 6 to 2021-05-01 Fr 7; 2021-05-01 Mo 10 to 2021-05-01 Th 13; 2021-05-01 Mo 17 to 2021-05-01 Tu 18
4 | UAT | 8 days | To-do | 2021-05-07 | 2021-05-19 | Pheang, Chenda, Bengsea | bar: 2021-05-01 Fr 7; 2021-05-01 Mo 10 to 2021-05-01 Th 13; 2021-05-01 Mo 17 to 2021-05-01 We 19
5 | Apply Feedback from Testign | 3 days | To-do | 2021-05-17 | 2021-05-19 | Em, Chanthourn, Roth, Kin | bar: 2021-05-01 Mo 17 to 2021-05-01 We 19
6 | Prepare Guild line | 2 days | To-do | 2021-05-20 | 2021-05-21 | Training | bar: 2021-05-01 Th 20 to 2021-05-01 Fr 21
7 | Prepare Memo and Approval | 2 days | To-do | 2021-05-20 | 2021-05-21 | Pheang | bar: 2021-05-01 Th 20 to 2021-05-01 Fr 21
8 | Staff Trainning | 2 days | To-do | 2021-05-23 | 2021-05-24 | Training
9 | Request Roll out | 1 day | To-do | 2021-05-20 | 2021-05-20 | Seyha | bar: 2021-05-01 Th 20
10 | Deploy Production | 1 day | To-do | 2021-05-28 | 2021-05-28 | Kin | bar: 2021-05-01 Fr 28
11 | Business Effective Date |  | To-do | 2021-05-30 |  | Seaksrun | bar: 2021-05-01 Mo 31
In-Progress Task
Planning Task
Closed Task
Delayed Task
Today

## Outsource byJason
Enhancement Prospect and CO/AM Schedule
[8 empty] | 2021-04-21 | [16 empty] | 2021-05-01 | [30 empty] | 2021-06-01 | [29 empty] | 2021-07-01 | [30 empty] | 2021-06-01
No | Task Name | Duration | Status | Start | Finish | Resource Names | Completed | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
1 | Requirement Collection & Documentation |  | Closed |  |  | Seyha I. | 100% | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 10 | 11 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
1.1 | Business Requirement Collection |  | Closed |  |  |  | 100% | 2021-04-21 We: Cambodia's Holiday (Khmer New Year); 2021-04-21 Mo: Cambodia's Holiday (វិសាខបូជា); 2021-04-21 Fr: Cambodia's Holiday (ច្រត់ព្រះនង្គ័ល); 2021-05-01 Sa: Cambodia's Holiday (ពលកម្មអន្ដរជាតិ); 2021-05-01 Fr: Cambodia's Holiday (ទិវានៃការចាំ); 2021-06-01 Fr: Cambodia's Holiday (ទិវានៃការចាំ)
1.2 | Requirement and Sign (FSD) |  | Closed |  |  |  | 100%
2 | MIS Team Development |  | To-do |  |  | Kin & Roth
2.2 | Backend API Development |  | To-do
2.3 | Tab Switch Web development |  | To-do
3 | Jason Team Development (Tablet App) |  | To-do |  |  | Jason T.
3.1 | Project Preparationn | 3 Days | In-Progess | bar: 2021-04-21 We to 2021-04-21 Fr
3.2 | Review the existing source code and structure | 4 Days | To-do | bar: 2021-04-21 Tu to 2021-04-21 Th; 2021-05-01 Mo
3.3 | Prospect Reject Status | 2 Days | To-do | bar: 2021-05-01 Tu to 2021-05-01 We
3.4 | Add new fields in prospect screen | 3 Days | To-do | bar: 2021-05-01 Th to 2021-05-01 Fr; 2021-05-01 Mo
3.5 | View / Filter Calendar | 36 Days | To-do | bar: 2021-05-01 Tu to 2021-05-01 Th; 2021-05-01 Mo to 2021-05-01 Fr; 2021-05-01 Mo to 2021-05-01 Fr; 2021-05-01 Mo to 2021-06-01 Fr; 2021-06-01 Mo to 2021-06-01 Fr; 2021-06-01 Mo to 2021-06-01 Th; 2021-06-01 Mo to 2021-06-01 Fr; 2021-06-01 Mo to 2021-07-01 Th
3.6 | View Detail Holiday | 3 Days | To-do | bar: 2021-07-01 Fr; 2021-07-01 Mo to 2021-07-01 Tu
3.7 | View Schedule Task | 3 Days | To-do | bar: 2021-07-01 We to 2021-07-01 Fr
3.8 | Add / Update / Update Schedule Task | 11 Days | To-do | bar: 2021-07-01 Mo to 2021-07-01 Fr; 2021-07-01 Mo to 2021-07-01 Fr; 2021-07-01 Mo
3.9 | Notification Reminder | 3 Days | To-do | bar: 2021-07-01 Tu to 2021-07-01 Th
3.10 | System intergation test | 3 Days | To-do | bar: 2021-07-01 Tu to 2021-07-01 Th
4 | SIT |  | To-do |  |  | Pheara
5 | UAT |  | To-do |  |  | Chenda, Pheang and Training
6 | Apply Feedback from Testign |  | To-do |  |  | MIS and Jason team
7 | Prepare Guild line |  | To-do |  |  | Training
8 | Prepare Memo and Approval |  | To-do |  |  | Pheang
9 | Staff Trainning |  | To-do |  |  | Training
10 | Request Roll out |  | To-do |  |  | Seyha I.
11 | Deploy Production |  | To-do |  |  | Kin
12 | Business Effective Date |  | To-do |  |  | Srun
In-Progress Task
Planning Task
Closed Task
Delayed Task
Today

## Jason WBD
Enhancement Prospect and CO/AM Schedule
[6 empty] | Resource | 2021-04-21 | [16 empty] | 2021-05-01 | [30 empty] | 2021-06-01 | [29 empty] | 2021-07-01 | [30 empty] | 2021-06-01
Task No | Task Name | Duration(Day) | Status | Start | Finish | Resource | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su | Mo
Sprint 1 | [6 empty] | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 10 | 11 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
1 | Project Preparationn | 3 | In-Progess | 2021-04-21 | 2021-04-23 | Jason | 14: Cambodia's Holiday (Khmer New Year); 26: Cambodia's Holiday (វិសាខបូជា); 30: Cambodia's Holiday (ច្រត់ព្រះនង្គ័ល); 1: Cambodia's Holiday (ពលកម្មអន្ដរជាតិ); 14: Cambodia's Holiday (ទិវានៃការចាំ); 18: Cambodia's Holiday (ទិវានៃការចាំ)
2 | Review the existing source code and structure | 4 | To-do | 2021-04-27 | 2021-05-03 | Jason | bar: 27 to 29; 3
3 | Backend Edit API of prospect | 2 | To-do |  |  | MIS
4 | Prospect Reject Status | 2 | To-do | 2021-05-04 | 2021-05-05 | Jason | bar: 4 to 5
5 | Add new fields in prospect screen | 3 | To-do | 2021-05-06 | 2021-05-10 | Jason | bar: 6 to 7; 10
Sprint 2
6 | View / Filter Calendar (Year) | 12 | To-do | 2021-05-11 | 2021-05-27 | Jason | bar: 11 to 13; 17 to 21; 24 to 27
7 | Backend get holiday API | 2 | To-do
Sprint 3
8 | View / Filter Calendar (Month) | 12 | To-do | 2021-05-28 | 2021-06-14 | Jason | bar: 28; 31 to 4; 7 to 11; 14
9 | Backend get/create/edit task | 5 | To-do
Sprint 4
10 | View / Filter Calendar (Week) | 12 | To-do | 2021-06-15 | 2021-07-01 | Jason | bar: 15 to 17; 21 to 25; 28 to 1
Sprint 5
11 | View Detail Holiday | 3 | To-do | 2021-07-02 | 2021-07-06 | bar: 2; 5 to 6
12 | View Schedule Task | 3 | To-do | 2021-07-07 | 2021-07-09 | bar: 7 to 9
Sprint 6
13 | Add / Update / Update Schedule Task | 11 | To-do | 2021-07-12 | 2021-07-26 | bar: 12 to 16; 19 to 23; 26
Sprint 7 | bar: 27 to 29
14 | Notification Reminder | 3 | To-do | 2021-07-27 | 2021-07-29
15 | System intergation test | 3 | To-do | 2021-07-30 | 2021-08-03 | bar: 30; 2 to 3
In-Progress Task
Planning Task
Closed Task
Delayed Task
Today