## Sheet1
2 | Doc.# | Review the existing source code and structure | 4 | To-do | 2021-04-27 | 2021-05-03 | Jason
3 |  | Backend Edit API of prospect | 2 | To-do |  |  | MIS
4 |  | Prospect Reject Status | 2 | To-do | 2021-05-04 | 2021-05-05 | Jason
5 |  | Add new fields in prospect screen | 3 | To-do | 2021-05-06 | 2021-05-10 | Jason
Sprint 2
6 |  | View / Filter Calendar (Year) | 12 | To-do | 2021-05-11 | 2021-05-27 | Jason
7 |  | Backend get holiday API + (7.3.1) -> Web: setup holiday + (7.3.1) -> API: provide holiday (Date (Fdate,EDate), Description (KH and EN)) - Done -> Add fileds - Done -> Api get data for Web - Done -> Api get data for Tablet - Done -> Api add/Edit/Del Web | 2 | To-do
Sprint 3
8 |  | View / Filter Calendar (Month) | 12 | To-do | 2021-05-28 | 2021-06-14 | Jason
9 |  | (7.2.1.2) Backend get/create/edit task + Done -> Task fields: see in (7.2.1.2) and 10.Appendix + Done -> Add drop field in Lookup + Done -> Data model + Api: - Add/Edit from Tab - Get: By owner (and All) from Tab | 5 | To-do
Sprint 4
10 |  | View / Filter Calendar (Week) | 12 | To-do | 2021-06-15 | 2021-07-01 | Jason
Sprint 5
11 |  | View Detail Holiday | 3 | To-do | 2021-07-02 | 2021-07-06
12 |  | View Schedule Task | 3 | To-do | 2021-07-07 | 2021-07-09
Sprint 6
13 |  | Add / Update / Update Schedule Task | 11 | To-do | 2021-07-12 | 2021-07-26
Sprint 7
14 |  | Notification Reminder | 3 | To-do | 2021-07-27 | 2021-07-29
15 |  | System intergation test | 3 | To-do | 2021-07-30 | 2021-08-03